## Sheet1
IS436 Group 7 - Estimated Project Timeline
Date | Tasks | Weekly Meeting Agenda
10/01 - 10/08 | 1. Deliverable 1 - System Request 2. Division of Work/Roles 3. GitHub Project Modification 4. Kanban Board 5. Set-Up GitHub Collaboration | 1. Discuss Project Proposal 2. Start Working on Deliverable 1 3. Get involved in the GitHub Project
10/09 - 10/15 | 1. Work on Deliverable 2 2. Work on Functional requirements 3. Work on Non-functional Requirement 4. Start thinking of interview information 5. Create a set of questions for the interview 6. Implement Feedback from D1 | 1. Start thinking of deliverable 2 2. Think of requirements for the project 3. Get some Use Cases 4. Division of Work 5. Think of interviews
10/16 - 10/22 | 1. Work on interview and documentation 2. Get observation notes 3. Documentation of all resources and questions used 4. Use case analysis 5. Use case diagram 6. Implement Feedback from D1 7. Finish and Submit Deliverable 2 | 1. Interview, Interview, Interview 2. Documentation
10/23 - 10/29 | 1. Work on Deliverable 3 2. Start Working in Developing the project 3. Website Design 4. ERD Documentation 5. Implement Feedback from D2 | 1. Division of work 2. Making UI/UX Designs for the website 3. Thinking of database 4. Working in ERD
10/30 - 11/05 | 1. Write Initial Code/Web Dev 2. HTML/CSS/JS/Frameworks 3. Work on Functionality 4. Implement Feedback from D2 5. Finish and Submit Deliverable 3 | 1. Discuss web development and tools that will be used 2. Division of work 3. Start writing initial web dev codes
11/06 - 11/12 | 1. Work on Deliverable 4 2. Work on backend 3. Start working on a database 4. Implement Feedback from D3 | 1. Test, Test, Test, Test, Test 2. Division of work 3. Integration of code 4. Quality Assurance Test, Test, Test
11/13 - 11/19 | 1. Finish Backend Code 2. Finish Database 3. Implement Feedback from D3 4. Finish and Submit Deliverable 4 | 1. Test, Test, Test, Test, Test 2. Integration of Code 3. Division of Code 4. Finalize the backend and Database
11/20 - 11/26 | 1. Work on Deliverable 5 2. Quality Assurance Check 3. Bug fixes and Debugging 4. Implement Feedback from D4 | 1. Test, Test, Test, Test, Test 2. Integration of code 3. Division of work 4. Fix any potential bugs and error
11/27 - 12/3 | 1. Finalize the project 2. Finish All documentation 3. Implement Feedback from D3 4. Finish and Submit Deliverable 4 5. Work on Presentation | 1. Test, Test, Test, Test, Test 2. Finalize the web app 3. Check for any final errors or bugs 4. Plan for project presentation
12/04 - End of class | 1. Submission of All Documentation and Deliverables 2. Project Presentation | 1. Meet up before presentation 2. Presentation DEMO 3. Celebrate Project Completion